## Slide 1: Proposed 2014 RTF Work Plan and 3-year Look Back October 31, 2013

## Slide 2: Work Plan Development Process
RTF 2014 work plan Process | Date
Develop draft work plan and present to Operations subcommittee | Friday, September 4, 2013
Incorporate Operations subcommittee feedback and present draft work plan to RTF | Tuesday, September 17, 2013
Solicit comments on draft work plan from RTF members, the public, and Council (Council directs PAC to review) | Wednesday, September 18, 2013
Receive comments on draft work plan from RTF and public | Monday, October 7, 2013
Post comments and proposed final work plan to October RTF agenda | Tuesday, October 8, 2013
Present final proposed work plan to RTF and develop recommendations | Tuesday, October 15, 2013
Call with P4 to inform of work plan status and recommendations before presenting to Council | Monday, October 21, 2013
Send recommendations from RTF to Council (in Council packet) | Tuesday, October 29, 2013
RTF PAC reviews RTF-adopted work plan and sends recommendations to Council | Thursday, October 31, 2013
Present work plan to Council for approval | Tuesday, November 5, 2013

## Slide 3: Overarching theme: No major changes
Allocation among work plan categories is similar to 2013
Contract Staff Model working well and plan to continue using in-house staff
3rd party QA/QC review lending credibility and transparency; plan to continue
Pacing is adequate for measure reviews

## Slide 4: Proposed 2014 work plan
 | Proposed 2014 |  |  |  |  | 
Category | Contract RFP 2014 | RTF Contract Staff 2014 | Subtotal Funders 2014 | Council In-Kind Contribution 2014 | % of total | 
Existing Measure Review & Updates | $65,500 | $410,000 | $475,500 | $7,500 | 32% | 50%
New Measure Development & Review of Unsolicited Proposals | $65,000 | $140,000 | $205,000 | $3,000 | 14% | 
Standardization of Technical Analysis | $40,000 | $19,000 | $59,000 | $1,100 | 4% | 
Tool Development | $65,000 | $120,000 | $185,000 | $25,000 | 13% | 22%
Research Projects & Data Development | $60,000 | $60,000 | $120,000 | $42,500 | 8% | 
Regional Coordination | $12,500 | $6,000 | $18,500 | $6,000 | 1% | 
Website, Database support, Conservation Tracking | $25,000 | $40,000 | $65,000 | $75,000 | 4% | 28%
RTF Member Support & Administration | $145,000 | $0 | $145,000 | $5,000 | 10% | 
RTF Management | $4,000 | $196,000 | $200,000 | $112,000 | 14% | 
Subtotal New Work | $482,000 | $991,000 | $1,473,000 | $277,100 | 100% | 100%
 | 33% | 67% |  |  |  | 

## Slide 5: Changes in Work Plan from 2013
Slight decrease in existing measure review category
  Staff tackling legacy measure reviews on time
Keeping Contract Staff Model
  Bulk of measure review and development done in-house by RTF contract staff
Continue to contract out 3rd party QA/QC review of RTF staff work products
Several work plan items still contracted out via RFP
  Research projects, tool development, etc.

## Slide 6: Comments Received
Added funds for creation of searchable measure application database
  Decreased funds from standard protocols for this
Increased funds for more staff review of 7th plan assumptions
Added inflation rate for out-year projections
Increased funds for more tool refinement
  ECAM and ELCAP database
Request to look at facilitation training for staff

## Slide 7: 3-year Look Back at Allocation
Chart: 
| Technical Analysis | Tool Development, Research, Regional Coordination | Administration
2013 Breakdown | 0.51807 | 0.2226 | 0.25933
Chart: 2012 Breakdown
| Technical Analysis | Tool Development, Research, Regional Coordination | Administration
2012 Breakdown | 0.534 | 0.28 | 0.186
Chart: 
| Technical Analysis | Tool Development, Research, Regional Coordination | Administration
2014 Breakdown | 0.50204 | 0.21962 | 0.27834
Increase in Administration in 2013 due to added manager position
Increase in Administration in 2014 due to added website functionality
Reduction in Technical Analysis in 2014 due to less legacy measure review needed

## Slide 8: RTF Budgets – Contract RFP Allocation
Chart: 
| Contract RFP 2012 | Contract RFP 2013 | Contract RFP 2014
RTF Management | 4910 | 2946 | 4000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 25000
Regional Coordination | 0 | 19640 | 12500
Research Projects & Data Development | 176760 | 124714 | 60000
Tool Development | 84452 | 55974 | 65000
Standardization of Technical Analysis | 131588 | 43208 | 40000
New Measure Development & Review of Unsolicited Proposals | 99182 | 90344 | 65000
Existing Measure Review & Updates | 392800 | 118331 | 65500

## Slide 9: RTF Budgets – Contract Staff Allocation
Chart: 
| RTF Contract Staff 2012 | RTF Contract Staff 2013 | RTF Contract Staff 2014
RTF Management | 98200 | 208184 | 196000
RTF Member Support & Administration | 0 | 0 | 0
Website, Database support, Conservation Tracking | 0 | 0 | 40000
Regional Coordination | 56956 | 65794 | 6000
Research Projects & Data Development | 47136 | 24451.8 | 60000
Tool Development | 47136 | 37316 | 120000
Standardization of Technical Analysis | 41244 | 22095 | 19000
New Measure Development & Review of Unsolicited Proposals | 36334 | 67758 | 140000
Existing Measure Review & Updates | 85434 | 421376.2 | 410000

## Slide 10: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500

## Slide 11: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Increase due to new measures being submitted and increased staff review effort

## Slide 12: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Decrease due to reduction in effort on Guidelines once complete in late 2012

## Slide 13: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Changes due to increased tool development and efforts to simplify

## Slide 14: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Increase due to hiring RTF manager, website functionality, and more processes to manage

## Slide 15: Council Impact
Continual shift of technical & management work to RTF staff
  Reliant on Tom & Charlie for technical & management guidance – but much less analysis & implementation
  In-kind contribution still remains substantial ($275,000) = ~2 FTE Council staff
Heavily rely on Council for:
  IT assistance, database, website development & hosting
  Contracts development
  Accounting
  Administration of meeting space & setup
  Legal (charter, by-laws, contract review)

## Slide 16: High Level Staff Observations
Majority of budget allocated to in-house contract staff
  Much improved throughput & depth of analysis
  Significant cost savings in $/output compared to an all-RFP model
Work products using in-house staff have been more consistent, requiring less re-work
  Guidelines have helped greatly with this effort
  Cohesive staff team & intra-staff review adds quality
Suggestion by PAC to add 3rd party QC to RTF work products has led to better sourcing and documentation
  No major flaws have been uncovered in reviews

## Slide 17: High Level Staff Observations
RTF voting members becoming more familiar with Guidelines requirements and meaning of terms
  Staff able to more easily assess workload because of this
Current level of contract staff is likely sufficient for 2014 work
  Future projections show more staff may be needed
More subcommittee work is needed
  Complex work products will likely be reviewed in subcommittee instead of full RTF
  Adds needed level of staff support to facilitate, prepare, and summarize for full RTF
Standardization of processes is improving
  In-house staff has helped increase transparency

## Slide 18: PAC Recommendation from 2013
“…independent check on whether in-house contract staff [were] appropriately delegating to outside contracts when prudent to ensure that that independence and objectivity of the work is not compromised.”
Staff has been able to tackle measure update tasks
  However, has delegated tasks that require expertise in certain areas:
    Wood emissions quantification
    Refrigeration systems sensitivity analysis
    Evaluation subcommittee facilitation
    Tool development (SEEM, ProCost, ECAM)

## Slide 19: RTF Member Feedback on Business Model
Conducted online survey of RTF Voting and Corresponding members
Intended to gain feedback on:
  Use of new business model (i.e. in-house staff)
  Performance of RTF staff contractors
  Desire to continue with current staff selections

## Slide 20: RTF Member Feedback on Business Model
Additional Comments:
Even with outside staff, inside staff ended up filtering and improving contractor product.
The use of in-house staff is much better in regards to consistency, guideline compliance and timeliness. It will only improve with time in these areas.
I believe the technical analysis is better in most cases, though outside expertise may be stronger in some specific areas.
Chart: 
| Quality of analysis and workbook development | Timeliness of work products | Consistency of work products | Presentation completeness | Competence in technical analysis | Communication of complex issues to RTF | Alignment of work products/analysis with Guidelines
N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0
About the same using in-house staff | 4 | 5 | 2 | 8 | 9 | 5 | 1
Worse using in-house staff | 0 | 1 | 0 | 0 | 0 | 0 | 0
Better using in-house staff | 13 | 11 | 15 | 10 | 8 | 13 | 16

## Slide 21: RTF Member Feedback on Business Model
Assuming the RTF is going to stick with the in-house contract staff model for 2014, would you prefer to keep the same in-house contract staff on board? Or would you prefer to open a competitive bid solicitation to look for different staff? Please indicate why you prefer either option. |  |  | 
Answer Options | Response Percent | Response Count | 
Keep current staff on-board for 2014 | 100.0% | 20 | 
Solicit for new staff for 2014 | 0.0% | 0 | 
I prefer the above option because: |  | 17 | 
answered question: |  | 20 | 
skipped question: |  | 5 | 
Additional Comments:
They are doing a good job and it takes a long time and lots of money to train new staff.
We need to establish commitment and consistency with good staff so that we do not lose them to a job that may seem more "permanent".
Please keep the same staff on board. They are doing an incredible job.
Knowledge of the process, standards and measures is a key investment that's already been made in the existing staff.
The breadth of competencies seems sufficient for the work that needs to be completed.

## Slide 22: RTF Member Feedback on Business Model
General responses to “How are staff doing?”
  I am so impressed with the team that has been developed. The RTF is doing work on a level we have never seen before. Processes are being streamlined, and we are able to dig in and focus on critical issues. I very much support continuing this model into the future.
  We should have hired help sooner!! I feel they are an asset to the RTF.
  Doing a great job. One other benefit of in-house staff is I know who all of them are, as opposed to a wider network of outside contractors, each with their own internal teams, etc that might not be accessible.

## Slide 23: Contact
For more information, contact:
  Nicholas O’Neil, P.E.
  Northwest Power and Conservation Council
  851 SW 6th Ave
  Suite 1100
  Portland, OR 97204
  noneil@nwcouncil.org
  503.820.2312