## 2011 Final Budget
2011 RTF Work plan & Budget
Work Description |  | Completion Date | CY 2011 Sponsor Budget (Final) | RTF Contractors | RTF Staff | WHO | CY 2011 Budget | CY 2012 Budget | CY 2013 Budget | CY 2014 Budget | 4-Year Budget Total (2011-2014) | Notes on Out-Year Projections | Related 6th Plan Action Items
New Projects | End-Use Load Study - Phase 2a. In 2011 the subcommittee will to help develop the business case for why this research is needed, work with regional interests to put together a multi-year research plan and develop appropriate funding for the research. Recommendations will build on results of phase 1, completed in 2009, which cataloged available data sources, identified major data gaps and proposed possible next steps to update end use load data and to build an end use load data warehouse. | Ongoing | 100000 | 100000 | 0 | contractor | 100000 | 300000 | 100000 | 100000 | 600000 | No significant primary data collection in the out-year budget. Budget assumes the relatively costly funding for data collection activities is outside the RTF. The RTF budget does include ongoing data warehouse development and maintenance, data analysis for RTF and participating in collaborative efforts on research design to collect primary data where needed. Steady funding would allow for large-scale multi-year projects and/or small and medium projects as needed. | CONS-21
| Deemed Measures Review and Standardized Protocols. Continue reviewing, documenting and developing deemed measures and standardized protocols. | Ongoing | 500000 | 475000 | 25000 | contractor(s) | 500000 | 500000 | 250000 | 250000 | 1500000 | Three years at $500K to develop systematic approach and to cycle once through all RTF measures. Then scaling back to maintenance-level activity. | CONS-9, CONS-10
| Guidelines for Measure Costs & Non-Energy Benefits. Develop consistent methodologies and guidelines for estimating measure costs and non-energy benefits. | 2011 | 100000 | 100000 | 0 | contractor | 100000 | 50000 | 50000 | 50000 | 250000 | Develop approach and standards 2011. Maintenance and updates 2012-2014. | CONS-9, CONS-10
| Provide Direction for Measure Life. Provide the Region with better direction for determining measure life. Perform a literature review of measure life & develop recommendations for a methodology. | 2011 | 60000 | 60000 | 0 | contractor | 60000 | 10000 | 10000 | 10000 | 90000 | Assumes continuing implementation of the measure life methodology for new measures and revisions of measure lives for existing measures as new data become available. | CONS-9, CONS-10
| Identify Measures and Standardized Protocols that are applicable to small and/or rural utilities. | Ongoing | 20000 | 20000 | 0 | contractor | 20000 | 20000 | 20000 | 20000 | 80000 | Continued support. | CONS-17
Ongoing Projects | RTF Website. Significant refinements to the RTF website, including RFP and ongoing study information, PTCS provider and specifications information, and up-to-date meeting information. | Ongoing | 5000 | 0 | 5000 | Council Staff, RTF Staff | 5000 | 5000 | 5000 | 5000 | 20000 | Continued support of website. | CONS-8 CONS-21
| PTR Support. Uploading data to the PTR and perform the required QA/QC. Work with BPA and others to develop inputs. Error tracking. | Ongoing | 15000 | 0 | 15000 | Council Staff, RTF Staff | 15000 | 0 | 0 | 0 | 15000 | Ongoing work. | CONS-19
| EE Central Support. |  | 5000 | 0 | 5000 | Council Staff, RTF Staff | 5000 | 15000 | 15000 | 15000 | 50000 |  | CONS-19
| Regional Conservation Progress Tracking. | Ongoing | 5000 | 5000 | 0 | Council Staff, RTF contractor | 5000 | 5000 | 5000 | 5000 | 20000 | Ongoing work. | CONS-19
| Measure and Protocol Reviews. Ongoing RTF work to review new measures & technologies and revisions/updates to existing measures, including, but not limited to: - Consumer Electronics: review NEEA's deemed savings estimates - Exterior Lighting - Grocery Measures: Ongoing review of deemed savings. - New Manufactured Homes - Ductless heat pumps - Heat pump water heaters - Metering study for low flow faucet aerators in commercial restrooms | Ongoing | 200000 | 150000 | 50000 | RTF staff, RTF contractors, Council Staff | 200000 | 300000 | 300000 | 300000 | 1100000 | Ongoing work. | CONS-2, CONS-9, CONS-10
| Information Technology (IT) Standardized Protocol Review and Adoption. Hire a contractor to represent the RTF in developing RTF approved protocols, working with IT industry, BPA, and others. Initial work will determine focus of future work scope: larger server farms, small/medium sized systems, or both. | 2011 | 80000 | 80000 | 0 | Council Staff, RTF contractor | 80000 | 0 | 0 | 0 | 80000 | Majority of work on 2011. | CONS-2, CONS-9, CONS-10
RTF Support | RTF Members and Corresponding Members meeting and project support. Subcommittees and special measure reviews. |  | 150000 | 150000 | 0 | RTF members, corresponding members | 150000 | 150000 | 150000 | 150000 | 600000 |  | CONS-8
| RTF Meetings. (phone, lunches, minutes) | Ongoing | 20000 | 20000 | 0 | RTF staff | 20000 | 20000 | 20000 | 20000 | 80000 | Ongoing. | CONS-8
| Technical Contract Management. | Ongoing | 100000 | 10000 | 90000 | RTF staff, Council Staff | 100000 | 100000 | 100000 | 100000 | 400000 | Ongoing work. | CONS-8
| RTF Management. Planning, tracking, and organizing RTF affairs. Develop meeting agendas, subcommittee meetings, minor projects, special requests and inquiries, budgeting, and other management activities. | Ongoing | 35000 | 0 | 35000 | RTF staff | 35000 | 35000 | 35000 | 35000 | 140000 | Ongoing work. | CONS-8
| Revise RTF charter, establish by-laws, document procedures. Update operational documents to align them with current practices, respond to NEET review and subsequent recommendations. | Ongoing | 5000 | 0 | 5000 | RTF staff; Council staff | 5000 | 0 | 0 | 0 | 5000 |  | CONS-8
| Total |  | 1400000 | 1170000 | 230000 |  | 1400000 | 1510000 | 1060000 | 1060000 | 5030000
Council Staff - In-kind Contributions
| Technical Staff Support |  | 82600
| Administrative Support |  | 105000
| Meeting Facilities/Support |  | 50000
| Total NPCC In-Kind |  | 237600
| Total RTF Sponsor plus NPCC In-Kind Support |  | 1637600
Definitions
RTF Staff - Contract Staff for RTF Management (Adam) & Additional Staff beginning 2011
Council Staff - Tom, Charlie, Gillian, legal and administrative staff
RTF Members
RTF corresponding members
Contractors - Contracts for RTF projects

## 2011 Proposed Funding
Funding Level | 1400000
Organization | NEEA Funding Shares as of January 2010 | Share of RTF Budget | Proposed Contribution to RTF Budget Rounded
Bonneville Power Administration | 35.49% | 496875.3781 | 496900
Energy Trust of Oregon | 20.53% | 287363.4099 | 287400
Puget Sound Energy | 13.72% | 192052.6375 | 192100
Idaho Power Company | 8.617% | 120641.1128 | 120600
Avista Corporation, Inc | 5.53% | 77422.1139 | 77400
PacifiCorp | 4.508% | 63111.1871 | 63100
NorthWestern Energy | 3.813% | 53379.7569 | 53400
Seattle City Light | 3.721% | 52091.7735 | 52100
Clark Public Utilities | 1.36% | 19034.9929 | 19000
Tacoma Power | 1.124% | 15742.0195 | 15700
PUD #1 of Snohomish | 0.7871% | 11019.4136 | 11000
Eugene Water and Electric Board | 0.5185% | 7259.1446 | 7300
PUD #1 of Cowlitz County | 0.2862% | 4007.0595 | 4000
Total | 100% | 1400000 | 1400000
Note on D8: Charlie Grist: Added rounding loss of $1000 to Puget.